## Sheet1
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Lewis | Lit Review + Gantt Chart |  | Login System |  |  | Test Plan+Log |  | Complete Testing | Report Organiastion | Write Evaluation
Will | Lit Review | Aims and objectives + Class and sequance diagrams | Sidebar GUI | Filtering | Sorting | Machine learning | Implementation report | Implementation report
Yasen
Yamin | Report | Requirement | About page | GUI | Risk register | Testing |  | Editing patient data on GUI | Main Report
Yeyilo |  | Intriduction and requirements | Requirements |  | Risk report |  |  | Editing patient data on GUI | Making the presentation | Editing the presentation